## Communication Plan
Communications plan template for project: Marketing Data Application
Communications item forum (What) | Owner (Who-Sender) | Audience (Who-Receiver) | Timing (When) | Format medium (How) (Where) | Purpose (Why)
Sponsor 1:1 meeting | Srikanth | Rakeshsarma K | Weekly, Friday at 2pm, Continuous | Conference room | Update on the project status, changes we have made and deadlines
Project weekly status meeting | Rakeshsarma K | Srikanth, SaiTeja, Subhash | Two times in week, Tuesday, Saturday at 4 pm, continuous | Rakeshsarma K's office | Milestones achieved, Issues, review change requests etc..
Change(requests) control board | Rakeshsarma K | All Stakeholders | Weekly, wednesday at 9pm, Continuous | Virtual, Rakeshsarma K's office(sometimes) | Updated strategy plan, time line for the changes, cost and risks assiciated with it.
Trainings(IT Systems) | Rakeshsarma K | SaiTeja, Subhash | Weekly, Monday 12 pm, three times(Dynamic) between the project timeline | Main conference room | Discussion about new technologies(impact), training status of new employees, user interface updates in the app.
Vendor selection | Rakeshsarma K | Pranav | May 17, Monday 3 pm, One time | Rakeshsarma K's office | Discussion about resources includes IT support, quality team members and vendor for conference room maintainence.
Quality status meeting | Teja, Subhash | All Stakeholders | Weekly, Thursday at 3 pm, continuous | Teja's office | Latest updates on new app performance, feedback monitoring discussions etc.
Application launch room preparation | Teja | Rakeshsarma K, Teja, Subhash | Nov 15, Friday at 2 pm, One time | Conference room | Launch room preparation discussion things.
Version: 01 |  |  | Date: 01 Apr 2024