## Design Phase
Network Diagram for Designing Phase
Critical Path - 27 days
1.1.7 Finalize vendor contract
1 day
1.1.4 Solicit initial design feedback
3 days
1.1.1 Define key app functionality requirements
2 days
1.1.6 Gain final design approval
4 days
1.1.5 Update design based on feedback
10 days
1.1.3 Develop initial design
6 days
1.1.2 Identify vendor to design and develop app
3 days
Start
End
Buffer
1 day

## Development Phase
Network Diagram for Development Phase
Critical Path - Since, each task is dependent on the previous task we don't have critical path in this phase.
Numbered
activity
1.2.5 Implement IT upgrades
25 days
1.2.3 Solicit beta test feedback
3 days
1.2.6 Gain prototype sign-off
5 days
1.2.4 Update prototype based on feedback
10 days
1.2.2 Perform prototype beta test
10 days
1.2.1 Develop an initial prototype
25 days
Start
End
Buffer
2 day
1.2.7 Develop an app launch plan
10 days

## Testing Phase
Network Diagram for Testing Phase
Critical Path - Since, each task is dependent on the previous task we don't have critical path in this phase.
1.3.5 Gain customer acceptance
6 days
1.3.3 Begin full scale development
10 days
1.3.6 Approve the launch plan
3 days
1.3.4 Test the final app prototype
3 days
1.3.2 Train Marketing personnel on a new
5 days
1.3.1 Begin IT hiring
2 days
Start
End
Buffer
1 day

## Launch and Approve the App
Network Diagram for Launch and Approve the App Phase
Critical Path - 53 days
1.4.5 Implement app upgrades - 3 days
1.4.3 Monitor app performance
15 days
1.4.6 Plan v2 upgrades
10 days
1.4.4 Plan app upgrades
5 days
1.4.2 Launch a new app - 5 days
1.4.1 Finalize new hires
2 days
Start
End
1.4.7 Launch app v2
5 days
1.4.8 Complete the final project report
10 days
1.4.9 Document app issues
5 days