## Template
High-Level Budget: Resource Breakdown Structure Project Name: Marketing Data Application Date: 01 April 2024
WBS identifier # | Work package | Internal personal required | External personnel required | Venue costs | Materials required | Supplies required | Equipment required | Comments | Total direct costs
1.1.1 | Define key app functionality requirements | 500 | [5 empty] | Initial deposits | 500
1.1.2 | Identify vendor to design and develop app |  | 10000 |  |  |  |  | Hr | 10000
1.1.3 | Develop initial design |  |  |  | 300 |  | 500 | Planning | 800
1.1.4 | Solicit initial design feedback | 500 |  | 1000 |  |  |  |  | 1500
1.1.5 | Update design based on feedback |  | 10000 | [5 empty] | 10000
1.1.6 | Gain final design approval |  | 3000 | [5 empty] | 3000
1.1.7 | Finalize vendor contract |  | 1000 |  |  |  |  | Vendor recruitment | 1000
1.2.1 | Develop an initial prototype | 5000 |  | 500 | 600 |  | 500 | Team formation, Initial drafts and checks | 6600
1.2.2 | Perform prototype beta test | 10000 | [6 empty] | 10000
1.2.3 | Solicit beta test feedback | 300 | 300 | [5 empty] | 600
1.2.4 | Update prototype based on feedback | 6000 |  |  |  |  | 1000 |  | 7000
1.2.5 | Implement IT upgrades | 10000 | [6 empty] | 10000
1.2.6 | Gain prototype sign-off |  | 2000 |  |  |  |  | Project Sponsor sign-off | 2000
1.2.7 | Develop an app launch plan |  |  | 5000 |  |  | 2000 | IT/Software developer works, Lunch, Coffee, Computers, Databases etc. | 7000
1.3.1 | Begin IT hiring | 5000 | 2000 |  | 5000 | 1000 | 2000 |  | 15000
1.3.2 | Train Marketing personnel on a new app | [7 empty] | 0
1.3.3 | Begin full-scale development | 10000 | 3000 |  | 5000 |  | 2000 |  | 20000
1.3.4 | Test the final app prototype | 1000 | 500 | [5 empty] | 1500
1.3.5 | Gain customer acceptance |  |  | 2000 |  |  | 1000 | Feedback from customers | 3000
1.3.6 | Approve the launch plan |  | 2000 |  |  |  |  | Product Launch | 2000
1.4.1 | Finalize new hires | 50000 | 4000 |  | 5000 | 2000 |  | Hires/ HR | 61000
1.4.2 | Launch a new app | 5000 | 2000 | 10000 |  |  | 5000 | Application Lauch | 22000
1.4.3 | Monitor app performance | 1500 | 500 |  |  |  | 1000 | Monitoring app performances | 3000
1.4.4 | Plan app upgrades | 1000 | 500 | [5 empty] | 1500
1.4.5 | Implement app upgrades | 1000 | 400 |  |  |  | 500 |  | 1900
1.4.6 | Plan v2 upgrades | 1000 | 500 |  | 500 |  | 500 | Plan for the Launch | 2500
1.4.7 | Launch app v2 | 2000 | 1500 | 5000 | 2000 | 3000 | 1500 | Application Lauch | 15000
1.4.8 | Complete the final project report | 2000 | 1000 |  | 1500 |  | 500 | Closing/ Sign-off | 5000
1.4.9 | Document app issues | 1200 | 800 |  | 500 |  | 500 | Lessons learned | 3000
TOTAL COSTS |  | 113000 | 45000 | 23500 | 20400 | 6000 | 18500 | 0 | 226400
Contingency requirements (10%) | [8 empty] | 22640
Personnel cost requirements | [5 empty] | Note: Update cost categories to reflect actual project requirements
Rate | Name | Hours | Costs
100 | Train Marketing personnel on a new app | 20 | 2000
0
0
0
0
0
0
0
TOTAL |  |  | 2000