## Quality Management Plan
Quality management plan for project: Marketing Data Application
Part I: Project objectives (reference project charter)
1. Develop an initial app prototype
2. Perform initial beta test & Feedback gathering(2 weeks)
3. Provide trainings to new employees on the new app and update the changes in the app(1 week).
4. Launch the app (2 weeks)
5. Gather feedback( 1week)
6. Make necessary adjustments and monitor app performance(2 weeks)
7. Plan for version 2(2 weeks)
Part II: Project quality team (Project Manager, QA, QC, SME)
Name | Role | R (Responsible) | A (Accountable) | C (Consult) | I (Inform)
Rakeshsarma K | Project Manager | X | X
Teja | QA Lead | X | X | X | X
Subhash | QC Lead | X | X | X | X
SaiTeja | SME |  |  | X | X
Srikanth | SME |  |  | X | X
Quality assurance activities (quality audits) |  |  | Quality control activities (quality inpections)
Audit design process |  |  | Verify initial design
Audit development process |  |  | Verify initial beta test
Audit app verion 1 & 2 launch planning |  |  | Verify results from the test and update things
Audit feedback collection |  |  | Verify initial and final launch checklist