## Risk Register
Project: Marketing Data Application Date: 01 Apr 2024
# | Cause (condition/situation) | Event | Impact | Risk owner | Category | Probability risk rating | Impact risk rating | Risk score | Trigger | Response
1 | Design failure of new app | Launch app | Delay for app creation time | Sai Teja | T | 3 | 5 | 15 | Resources for designing the app are not received ontime | Have atleast 1 resource(IT developer) as a back-up.
2 | Initial beta test on the app | In office | Delay on the improvements of the app | Teja, Subhash | T | 2 | 3 | 6 | App didn't develop properly | Have checks at every stage while creating the app
3 | Trainings to the new employees on the app | Launch phase | Outcome of the new app didn't reach the expected level | Subhash | T | 1.5 | 4 | 6 | Training didn't happen properly because of their regular projects load. | Hire new people from outside not from internal teams.
4 | Feedback missed | Online | Delay in time and money because of the missed information which is used for improvements. | Srikanth | T | 2.5 | 2 | 5 | Feedback file stored in server got deleted | Don't provide access for delete the file to everyone in the team/company.
5 | Vendor selection | Design phase - Office | Quality of the new app will be decreased | Rakeshsarma K | T | 1 | 3 | 3 | If recommended vendor(Not qualified) would be selected | Try to get the vendor who is experienced
6 | App updation after receiving feedback | Improve phase - Office | Quality of the new app will be decreased | Srikanth | T | 1.5 | 1.5 | 2.25 | Employees are not willing to learn and implement new things in the app. | Try to motivate and explain them the importance of these updates and the project to the company.
7 | New App version 2 | Launch event | Attract new customers/business heads etc. | Teja | O | 4 | -4 | -16 | New app performance reached the expectations of the stakeholders | Create checklist at each stage to verify the performance.
Total Risk Score | [7 empty] | 21.25 | Risk Exposure
|  | Probability risk rating |  | Impact risk rating
|  | 5: High |  | 5: High
|  | 4: High to moderate |  | 4: High to moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to low |  | 2: Moderate to low
|  | 1: Low |  | 1: Low

## Risk Analysis
Risks | Impact | Prevent | How to prevent
Design failure of new app | Delay for app creation time | Yes | Have atleast 1 resource(IT developer) as a back-up.
Initial beta test on the app | Delay on the improvements of the app | Yes | Have checks at every stage while creating the app
Trainings to the new employees on the app | Outcome of the new app didn't reach the expected level | Yes | Hire new people from outside not from internal teams.
Feedback missed | Delay in time and money because of the missed information which is used for improvements. | Yes | Don't provide access for delete the file to everyone in the team/company.
Vendor selection | Quality of the new app will be decreased | Yes | Try to get the vendor who is experienced
App updation after receiving feedback | Quality of the new app will be decreased | Yes | Try to motivate and explain them the importance of these updates and the project to the company.
New App version 2 | Attract new customers/business heads etc. | Yes | Create checklist at each stage to verify the performance.
New equipment purchase | Additional cost | No | Make a plan on the materials we are having to complete the project.
Change requests | Delay in time and money because of addons in the project | No | Do in depth research about the implication of the data and the app.