## WBS
|  | 1.0 Marketing Data Application Development Project |  |  | Level 1 Project level
1.1 Design | 1.2 Development |  | 1.3 Testing | 1.4 Launch and Approve the App | Level 2 Phase level
1.1.1 Define key app functionality requirements | 1.2.1 Develop an initial prototype |  | 1.3.1 Begin IT hiring | 1.4.1 Finalize new hires | Level 3 Work package level
1.1.2 Identify vendor to design and develop app | 1.2.2 Perform prototype beta test |  | 1.3.2 Train Marketing personnel on a new app | 1.4.2 Launch a new app
1.1.3 Develop initial design | 1.2.3 Solicit beta test feedback |  | 1.3.3 Begin full-scale development | 1.4.3 Monitor app performance
1.1.4 Solicit initial design feedback | 1.2.4 Update prototype based on feedback |  | 1.3.4 Test the final app prototype | 1.4.4 Plan app upgrades
1.1.5 Update design based on feedback | 1.2.5 Implement IT upgrades |  | 1.3.5 Gain customer acceptance | 1.4.5 Implement app upgrades
1.1.6 Gain final design approval | 1.2.6 Gain prototype sign-off |  | 1.3.6 Approve the launch plan | 1.4.6 Plan v2 upgrades
1.1.7 Finalize vendor contract | 1.2.7 Develop an app launch plan |  |  | 1.4.7 Launch app v2
1.4.8 Complete the final project report
1.4.9 Document app issues